| Event Planning Guide – Let’s get Started |  |  |
| --- | --- | --- |
| Planning stage | Task | Notes/Highlights |
| 12th week | Event Idea Generation - What is the event? - Describe the purpose of the event - Who is the target market for this event? - When is the event (date and time?) - Is there an admission fee, if so how much? - Where is the event? - What will be happening at the event? - How many students should you plan for? | - Why you are having it and what you hope to achieve. - These questions should help you gain the necessary focus. - Begin to think about your budget – outline the components/ requirements and attach a cost |
|  | Co-Sponsorships - Meet with co-sponsors and discuss terms of sponsorship | - Clearly define your objectives. - How the sponsors’ objectives fit into your objectives - How the sponsors can benefit - Be open to discussion |
|  | Programming Meeting - Meet with the advisor for event development | ADVISORS: a good fit - Assists in achieving goals - Great interest in the organization - A resource person - Provide support “Staff/ faculty advisors are assets to your club, society/ association. Every club should have one.” |
|  | Marketing Meeting - Meet with marketing team to discuss strategies for the event - Include co-sponsors, if any | Flyers may be placed on the bulletin boards only Not permitted elsewhere |
| 10th week | Vendor \ Talent \ Catering Quotes - Begin gathering quotes, pricing estimates to help develop a realistic budget. - Identify technical requirements and supplies needed for event | What is your budget? Identify all the elements/requirements to execute your event |
|  | Finance Meeting - Create a budget - Meet with co-sponsors and describe each organization’s financial obligations, if any | The more information/line items identified the more accurate your budget will be Never under price items |
|  | Draft Letters - Draft proposal letter to the Director of OSS - Draft application letters for permits |  |
| 8th week | Event Proposal Submission - Submit proposal (soft copy ) to the Director of Student Services | Proposal must be inclusive of detailed budget |
| 7th-6th week | Event Proposal Review - Meet with the Student Activities Committee (SAC) to review the event proposal, budget, and co-sponsorship agreement(s). - Review and execute marketing timeline - Consider any changes or recommendations by the SAC | Use this time wisely to tighten your event |
| 5th week | Follow up - Update the SAC using the students activities table of any changes to the week based ONLY on their recommendations (other changes are not permitted) | Additional activities will not be considered at this stage |
| 4th week | Vendor \ Talent \ Catering Reservations - Contact all vendor \ talent \ catering to notify them that you will be using their services on what dates and times | Seek copies of their food and restaurant permits to be submitted to the OSS |
|  | Reserve Rooms/Locations - Check the availability of, and reserve rooms through Ms Laura Yard – Campus Registrar Office - Submit facilities request form to the OSS |  |
| 3rd week | Applications - Submit all applications to the relevant Departments - Food Handlers’ permit - Temporary Restaurant permit - Liquor License - Loud Noise permit - COSCAP - Liability Insurance request, if necessary | This process is critical, late submissions impacts the approval process Be considerate of stakeholders and their time |
| 2nd week | Volunteer Sign-up - Gather volunteers/members to help set up the event, work the event and tear down the event - Create event task assignments (what will each volunteer/member do?) |  |
|  | Vendor \ Talent \ Catering Ordering - Order all and pay for vendor \ talent \ catering needs. - Buy/Pick up all needed decorations |  |
|  | Guest Speakers/Foreign Dignitaries - Notify Ministry of Foreign Affairs, OSS and Assistant Registrar of Foreign Dignitaries visit and itinerary | See the OSS website for more information on this aspect of your planning |
| 1 week away | Permits - Pick up permit certificates - Provide copies of permit certificates to the OSS |  |
| 1st week after | Event Wrap Up - Return materials to storage - Gather receipts and invoices and document them for future events - Complete and submit a documented account including financial statement to the Director of Student Services, Campus Bursar, Registrar and Guild President - Write thank you notes, if appropriate |  |